## Sheet1
Category | Task | Owner | Due Date | Status | Notes | Status Key | Owner Text Key
Literature Review | Find 4 sources for TPP section | MA | 2020-05-01 | Overdue/Complete | Completed 5/4 (MA) | Not Started | Molly
Literature Review | Initial draft of TPP section (aprox. 1 page) | LM | 2020-05-05 | Complete |  | In Progress | Lindsay
Literature Review | Feedback on TPP section | NK | 2020-05-07 | Complete | Be sure to look at comments AND tracked changes (NK) | Completed on Time | Nick
Literature Review | Implement feedback | LM | 2020-05-10 | Overdue/Not Complete | Will complete by 5/11 at midnight (LM) | Overdue/Complete | Jeff
Literature Review | Final review of TPP section | NK | 2020-05-12 | Not Started |  | Overdue/Not Complete
Literature Review | Add to word document | NK | 2020-05-13 | Not Started |  | Overdue/In Progress
Literature Review | Add all sources to reference list | MA | 2020-05-13 | Not Started
Literature Review | Check formatting | MA | 2020-05-14 | Not Started